## Chat Conversations
Timestamp | Speaker | Message | Type
2025-08-16T09:29:29.023Z | Section 1 | SDLC Reorganization Plan - August 2025 **Date**: August 10, 2025 **Status**: Ready for Review **Purpose**: Separate product specifications from SDLC process artifacts | heading_1
2025-08-16T09:29:29.023Z | Section 2 | 📊 Current State Analysis | heading_2
2025-08-16T09:29:29.023Z | Section 3 | By the Numbers - **Total Files**: 149 - **Agent/Processor Files**: 58 (39%) - **User Stories**: 10 (7%) - **Potential Archives**: 33 (22%) - **Mixed Concerns**: 16 files in wrong locations | heading_3
2025-08-16T09:29:29.023Z | Section 4 | Key Problems Identified 1. **Mixed Concerns**: Product specs mixed with SDLC process files 2. **Duplicate Files**: Multiple versions of processors in archives 3. **Scattered State**: Session tracking in multiple locations 4. **Path Confusion**: Agents looking for files in wrong directories | heading_3
2025-08-16T09:29:29.023Z | Section 5 | 🎯 Reorganization Strategy | heading_2
2025-08-16T09:29:29.023Z | Section 6 | Core Principle: Separation of Concerns - **`.product-specs/`** = WHAT we build (features, requirements, user stories) - **`.sdlc/`** = HOW we build (agents, workflows, patterns, tools) | heading_3
2025-08-16T09:29:29.023Z | Section 7 | New Structure Overview ``` .product-specs/ # Product requirements ├── 00-platform-core/ # Shared across all domains │ ├── vision/ │ │ └── master-view-feature.md # From 05-backlog/ │ ├── epics/ │ │ └── EP-001-accounts/ │ │ ├── features/ │ │ │ ├── FEA-001-master-view/ │ │ │ │ └── stories/ # From 05-backlog/A-accounts/ │ │ │ └── FEA-002-reports/ │ │ └── architecture/ # Technical designs │ └── busm-model/ # Universal data model │ ├── 01-pest-control/ # Domain-specific └── 02-marine-services/ # Domain-specific .sdlc/ # Process & tools (cleaned up) ├── 01-core/ # Keep as-is ├── 05-active-work/ # Renamed from 05-backlog │ └── current-iteration/ # Symlinks to active story ├── 09-archive/ # Expanded │ ├── investigations-2025-08/ # From validation/completed │ └── old-processors/ # From G-agent-archive └── 10-project-tracking/ # NEW - Consolidated tracking ├── session-state.json # From 07-operations └── iteration-logs/ # From current-work ``` | heading_3
2025-08-16T09:29:29.023Z | Section 8 | 📋 Migration Plan | heading_2
2025-08-16T09:29:29.023Z | Section 9 | Phase 1: Safety First (10 minutes) ```bash | heading_3
2025-08-16T09:29:29.023Z | Section 10 | 1. Document current state git status git add -A git commit -m "Pre-reorganization snapshot - 149 files documented per audit" | heading_1
2025-08-16T09:29:29.023Z | Section 11 | 2. Create safety branch git checkout -b reorganization-2025-08-10 | heading_1
2025-08-16T09:29:29.023Z | Section 12 | 3. Tag current state git tag -a pre-reorg-v1 -m "State before product/SDLC separation" ``` | heading_1
2025-08-16T09:29:29.023Z | Section 13 | Phase 2: Create New Structure (15 minutes) ```bash | heading_3
2025-08-16T09:29:29.023Z | Section 14 | Product specifications mkdir -p .product-specs/00-platform-core/{vision,epics,busm-model} mkdir -p .product-specs/00-platform-core/epics/EP-001-accounts/{features,architecture} mkdir -p .product-specs/01-pest-control/features mkdir -p .product-specs/02-marine-services/features | heading_1
2025-08-16T09:29:29.023Z | Section 15 | SDLC improvements mkdir -p .sdlc/10-project-tracking/{iteration-logs,metrics} mkdir -p .sdlc/09-archive/{investigations-2025-08,old-processors,old-manifests} ``` | heading_1
2025-08-16T09:29:29.023Z | Section 16 | Phase 3: Move Product Files (20 minutes) ```bash | heading_3
2025-08-16T09:29:29.023Z | Section 17 | Move user stories and requirements git mv .sdlc/05-backlog/A-accounts/master-view/*.md .product-specs/00-platform-core/epics/EP-001-accounts/features/FEA-001-master-view/stories/ git mv .sdlc/05-backlog/A-accounts/list-view/*.md .product-specs/00-platform-core/epics/EP-001-accounts/features/FEA-002-reports/stories/ | heading_1
2025-08-16T09:29:29.023Z | Section 18 | Move vision document git mv .sdlc/05-backlog/master-view-feature.md .product-specs/00-platform-core/vision/ | heading_1
2025-08-16T09:29:29.023Z | Section 19 | Move architecture docs git mv .sdlc/08-architecture/C-ui-ux/*interaction*.md .product-specs/00-platform-core/epics/EP-001-accounts/architecture/ ``` | heading_1
2025-08-16T09:29:29.023Z | Section 20 | Phase 4: Archive Obsolete Files (15 minutes) ```bash | heading_3
2025-08-16T09:29:29.023Z | Section 21 | Archive completed investigations git mv .sdlc/validation/investigations/completed/* .sdlc/09-archive/investigations-2025-08/ | heading_1
2025-08-16T09:29:29.023Z | Section 22 | Archive old processor versions (already in G-agent-archive) git mv .sdlc/01-core/G-agent-archive/* .sdlc/09-archive/old-processors/ | heading_1
2025-08-16T09:29:29.023Z | Section 23 | Archive old manifests git mv .sdlc/05-backlog/A-accounts/master-view/processor-manifest-vs*.json .sdlc/09-archive/old-manifests/ ``` | heading_1
2025-08-16T09:29:29.023Z | Section 24 | Phase 5: Consolidate Tracking (10 minutes) ```bash | heading_3
2025-08-16T09:29:29.023Z | Section 25 | Move session tracking git mv .sdlc/current-work/* .sdlc/10-project-tracking/iteration-logs/ git mv .sdlc/07-operations/A-session-tracking/session-state.json .sdlc/10-project-tracking/ | heading_1
2025-08-16T09:29:29.023Z | Section 26 | Clean up empty directories git rm -r .sdlc/current-work git rm -r .sdlc/05-backlog/A-accounts ``` | heading_1
2025-08-16T09:29:29.023Z | Section 27 | Phase 6: Update References (30 minutes) This requires manual updates to: 1. Agent prompts - Update file paths 2. Import statements in code 3. Documentation references 4. Scripts that reference old paths | heading_3
2025-08-16T09:29:29.023Z | Section 28 | 🔍 Validation Checklist | heading_2
2025-08-16T09:29:29.023Z | Section 29 | Before Migration - [ ] All files committed to Git - [ ] Safety branch created - [ ] Current state tagged - [ ] Team notified of changes | heading_3
2025-08-16T09:29:29.023Z | Section 30 | After Migration - [ ] No files lost (Git history preserved) - [ ] All user stories in product-specs - [ ] All SDLC tools remain in .sdlc - [ ] Archive is organized by date/type - [ ] Empty directories removed | heading_3
2025-08-16T09:29:29.023Z | Section 31 | Testing - [ ] One agent updated with new paths - [ ] Test agent can find required files - [ ] Git history accessible for moved files - [ ] No broken imports in codebase | heading_3
2025-08-16T09:29:29.023Z | Section 32 | 📊 Success Metrics | heading_2
2025-08-16T09:29:29.023Z | Section 33 | Immediate - Clean separation of concerns - Reduced file search time - Clear product backlog location - Organized archive structure | heading_3
2025-08-16T09:29:29.023Z | Section 34 | Long-term - Easier onboarding for new domains - Simplified Azure DevOps integration - Clearer product roadmap visibility - Improved SDLC maintenance | heading_3
2025-08-16T09:29:29.023Z | Section 35 | ⚠️ Risk Mitigation | heading_2
2025-08-16T09:29:29.023Z | Section 36 | Potential Issues 1. **Broken References**: Agent prompts with hardcoded paths - **Mitigation**: Update incrementally, test each agent 2. **Lost History**: Git might lose track of moved files - **Mitigation**: Use `git mv` exclusively, never manual move 3. **Import Errors**: Code imports using old paths - **Mitigation**: Global search/replace with verification 4. **Team Confusion**: Others don't know new structure - **Mitigation**: Update README, communicate changes | heading_3
2025-08-16T09:29:29.023Z | Section 37 | 🚀 Next Steps After Reorganization 1. **Update DevOps Agent** - First agent to use new paths 2. **Test US-005 Flow** - Verify end-to-end process works 3. **Document New Structure** - Update main README 4. **Create Path Constants** - Central config for all paths 5. **Azure DevOps Prep** - Map product-specs to work items | heading_2
2025-08-16T09:29:29.023Z | Section 38 | 📝 Notes for CC | heading_2
2025-08-16T09:29:29.023Z | Section 39 | Questions for Implementation 1. Should we create symlinks for backward compatibility temporarily? 2. Any files in the audit that shouldn't be moved? 3. Preferred order for updating agent references? 4. Should we automate the path updates with a script? | heading_3
2025-08-16T09:29:29.023Z | Section 40 | Expected Outcomes - Product owners can find all requirements in one place - SDLC team can evolve process without touching product specs - Clear handoff points between product definition and development - Foundation for multi-domain scaling --- *This plan separates concerns while preserving all Git history and maintaining system functionality.* | heading_3

## Summary
Metric | Value
Report Name | sdlc-reorg-plan
Sections | 40
Generated | 8/16/2025
Date | August 10, 2025
Status | Ready for Review
Purpose | Separate product specifications from SDLC process artifacts
Total Files | 149
Agent/Processor Files | 58 (39%)
User Stories | 10 (7%)
Potential Archives | 33 (22%)
Mixed Concerns | Product specs mixed with SDLC process files
Duplicate Files | Multiple versions of processors in archives
Scattered State | Session tracking in multiple locations
Path Confusion | Agents looking for files in wrong directories
Broken References | Agent prompts with hardcoded paths
Mitigation | Update README, communicate changes
Lost History | Git might lose track of moved files
Import Errors | Code imports using old paths
Team Confusion | Others don't know new structure