## Chat Conversations
Timestamp | Speaker | Message | Type
2025-08-16T09:29:29.176Z | Section 1 | SDLC Reorganization Execution Prompts **Date**: August 10, 2025 **Purpose**: Step-by-step prompts for safe reorganization | heading_1
2025-08-16T09:29:29.177Z | Section 2 | ⚠️ EXECUTION INSTRUCTIONS 1. **Execute prompts in STRICT order** 2. **STOP at each checkpoint for review** 3. **Do NOT proceed past a checkpoint without approval** 4. **Report issues immediately** | heading_2
2025-08-16T09:29:29.177Z | Section 3 | 🛑 CHECKPOINT SYSTEM - **GREEN CHECKPOINT** ✅ = Safe to proceed after CC reports - **YELLOW CHECKPOINT** 🟡 = Need human review before proceeding - **RED CHECKPOINT** 🔴 = STOP - Critical review required --- | heading_2
2025-08-16T09:29:29.177Z | Section 4 | 🚦 Phase 0: Pre-Flight (NEW - Based on CC's Analysis) | heading_2
2025-08-16T09:29:29.177Z | Section 5 | Prompt 1: Create Path Configuration System ``` @cc Please create the following path configuration system: 1. Create file: `.sdlc/config/path-config.json` with: ```json { "version": "1.0", "lastUpdated": "2025-08-10", "paths": { "manifestPath": ".sdlc/05-backlog/A-accounts/master-view/", "userStoriesPath": ".sdlc/05-backlog/A-accounts/", "sessionStatePath": ".sdlc/07-operations/A-session-tracking/", "currentWorkPath": ".sdlc/current-work/", "validationPath": ".sdlc/validation/", "processorsPath": ".sdlc/01-core/A-agents/processors/" }, "migration": { "status": "pre-migration", "symlinksActive": false } } ``` 2. Update these scripts to use path-config.json: - scripts/run-slice.sh - scripts/extract-value-slices.js - scripts/validate-processor-output.js - scripts/run-processor-pipeline.sh 3. Test that all scripts still work with current paths Report which scripts were updated and any that couldn't be found. ``` | heading_3
2025-08-16T09:29:29.177Z | Section 6 | ✅ CHECKPOINT 1: Path Configuration Review **Type**: GREEN - Safe to proceed after CC confirms: - [ ] path-config.json created successfully - [ ] All scripts updated to use config - [ ] Scripts tested and working - [ ] No hardcoded paths remain --- | heading_3
2025-08-16T09:29:29.177Z | Section 7 | Prompt 2: Audit All Path References ``` @cc Please audit all path references in the project: 1. Check package.json for any scripts with paths 2. Review all .github/workflows/*.yml files for path references 3. Find all README files with relative links that might break 4. Search for hardcoded paths in: - *.js, *.ts, *.jsx, *.tsx files - *.sh files - *.md files Output a report: `path-references-audit.md` listing all files that need updates. ``` | heading_3
2025-08-16T09:29:29.177Z | Section 8 | 🟡 CHECKPOINT 2: Path Audit Review **Type**: YELLOW - Need human review: - [ ] Review path-references-audit.md - [ ] Identify any critical paths CC found - [ ] Decide if any need manual handling - [ ] APPROVAL REQUIRED: "Proceed with Phase 1" --- | heading_3
2025-08-16T09:29:29.177Z | Section 9 | 🏃 Phase 1: Safety First | heading_2
2025-08-16T09:29:29.177Z | Section 10 | Prompt 3: Create Safety Checkpoint ``` @cc Please execute safety preparations: 1. Verify git status is clean: ```bash git status ``` 2. Create safety commit: ```bash git add -A git commit -m "Pre-reorganization checkpoint - 149 files per audit" ``` 3. Create and switch to reorganization branch: ```bash git checkout -b feature/sdlc-product-separation-2025-08 ``` 4. Tag current state: ```bash git tag -a pre-reorg-v1.0 -m "State before product/SDLC separation" ``` 5. Verify current work is complete: - Check if any active stories in progress - Confirm session-state.json is not mid-task Report status of each step. ``` | heading_3
2025-08-16T09:29:29.177Z | Section 11 | ✅ CHECKPOINT 3: Safety Verified **Type**: GREEN - Safe to proceed after: - [ ] Git status clean - [ ] Branch created - [ ] Current state tagged - [ ] No active work in progress --- | heading_3
2025-08-16T09:29:29.177Z | Section 12 | 📁 Phase 2: Create New Structure | heading_2
2025-08-16T09:29:29.177Z | Section 13 | Prompt 4: Build Target Directories ``` @cc Please create the new directory structure: ```bash | heading_3
2025-08-16T09:29:29.177Z | Section 14 | Product specifications structure mkdir -p .product-specs/00-platform-core/{vision,busm-model} mkdir -p .product-specs/00-platform-core/epics/EP-001-accounts/{features,architecture} mkdir -p .product-specs/00-platform-core/epics/EP-001-accounts/features/{FEA-001-master-view,FEA-002-reports}/stories mkdir -p .product-specs/01-pest-control/{domain-model,features} mkdir -p .product-specs/02-marine-services/{domain-model,features} | heading_1
2025-08-16T09:29:29.177Z | Section 15 | SDLC improvements mkdir -p .sdlc/09-archive/{investigations-2025-Q3,old-processors,old-manifests} mkdir -p .sdlc/10-project-tracking/{config,iterations/current,metrics,reports} mkdir -p .sdlc/11-reference/{patterns,templates,examples} | heading_1
2025-08-16T09:29:29.177Z | Section 16 | Add .gitkeep to empty directories find .product-specs .sdlc -type d -empty -exec touch {}/.gitkeep \; ``` List all created directories. ``` | heading_1
2025-08-16T09:29:29.177Z | Section 17 | ✅ CHECKPOINT 4: Structure Ready **Type**: GREEN - Verify: - [ ] All directories created - [ ] .gitkeep files added - [ ] No errors reported --- | heading_3
2025-08-16T09:29:29.177Z | Section 18 | 🗄️ Phase 3: Archive First (CC's Recommendation) | heading_2
2025-08-16T09:29:29.177Z | Section 19 | Prompt 5: Archive Obsolete Files ``` @cc Please archive obsolete files (CC's recommended order): 1. Archive old investigations (60-day retention per CC): ```bash | heading_3
2025-08-16T09:29:29.177Z | Section 20 | Move investigations older than 60 days git mv .sdlc/validation/investigations/completed/* .sdlc/09-archive/investigations-2025-Q3/ ``` 2. Archive old processor versions: ```bash git mv .sdlc/01-core/G-agent-archive/* .sdlc/09-archive/old-processors/ ``` 3. Archive OLD manifest versions (keep current processor-manifest.json): ```bash git mv .sdlc/05-backlog/A-accounts/master-view/processor-manifest-vs1.json .sdlc/09-archive/old-manifests/ git mv .sdlc/05-backlog/A-accounts/master-view/processor-manifest-vs2.json .sdlc/09-archive/old-manifests/ git mv .sdlc/05-backlog/A-accounts/master-view/processor-manifest-vs3.json .sdlc/09-archive/old-manifests/ ``` Report: files moved and confirm processor-manifest.json remains in place. ``` | heading_1
2025-08-16T09:29:29.177Z | Section 21 | 🟡 CHECKPOINT 5: Archive Complete **Type**: YELLOW - Verify critical files: - [ ] processor-manifest.json NOT moved (still active) - [ ] Only old versions archived - [ ] Investigation count matches expectation - [ ] APPROVAL REQUIRED: "Archive correct, proceed" --- | heading_3
2025-08-16T09:29:29.177Z | Section 22 | 📦 Phase 4: Move Product Specifications | heading_2
2025-08-16T09:29:29.177Z | Section 23 | Prompt 6: Migrate User Stories and Features ``` @cc Please move product-related files to new structure: 1. Move master view stories: ```bash git mv .sdlc/05-backlog/A-accounts/master-view/US-*.md .product-specs/00-platform-core/epics/EP-001-accounts/features/FEA-001-master-view/stories/ git mv .sdlc/05-backlog/A-accounts/master-view/us-*.md .product-specs/00-platform-core/epics/EP-001-accounts/features/FEA-001-master-view/stories/ ``` 2. Move reports view stories: ```bash git mv .sdlc/05-backlog/A-accounts/list-view/*.md .product-specs/00-platform-core/epics/EP-001-accounts/features/FEA-002-reports/stories/ ``` 3. Move vision document: ```bash git mv .sdlc/05-backlog/master-view-feature.md .product-specs/00-platform-core/vision/ ``` 4. Move architecture docs: ```bash git mv .sdlc/08-architecture/C-ui-ux/accounts-v1-interaction-design.md .product-specs/00-platform-core/epics/EP-001-accounts/architecture/ ``` 5. Keep processor-manifest.json in current location (per CC's advice) Report all moves completed and any errors. ``` | heading_3
2025-08-16T09:29:29.177Z | Section 24 | 🔴 CHECKPOINT 6: Product Files Moved **Type**: RED - CRITICAL REVIEW: - [ ] All user stories moved correctly - [ ] Vision document in right place - [ ] Architecture docs moved - [ ] Git history preserved (spot check) - [ ] APPROVAL REQUIRED: "Product separation complete" - [ ] DECISION POINT: Continue or rollback? --- | heading_3
2025-08-16T09:29:29.177Z | Section 25 | 🔄 Phase 5: Consolidate Tracking | heading_2
2025-08-16T09:29:29.177Z | Section 26 | Prompt 7: Centralize Project Tracking ``` @cc Please consolidate tracking files: 1. Move session state: ```bash git mv .sdlc/07-operations/A-session-tracking/session-state.json .sdlc/10-project-tracking/config/ ``` 2. Move current work tracking: ```bash git mv .sdlc/current-work/session-summaries .sdlc/10-project-tracking/reports/ git mv .sdlc/current-work/*.json .sdlc/10-project-tracking/iterations/current/ ``` 3. Create symlink for active iteration: ```bash ln -s iterations/current .sdlc/10-project-tracking/active ``` 4. Update path-config.json with new locations Report moves and verify session-state.json is accessible. ``` | heading_3
2025-08-16T09:29:29.177Z | Section 27 | 🟡 CHECKPOINT 7: Tracking Consolidated **Type**: YELLOW - Verify: - [ ] Session state accessible - [ ] Current work preserved - [ ] Symlinks working - [ ] APPROVAL REQUIRED: "Tracking structure good" --- | heading_3
2025-08-16T09:29:29.177Z | Section 28 | 🔧 Phase 6: Update References | heading_2
2025-08-16T09:29:29.177Z | Section 29 | Prompt 8: Update Path References ``` @cc Please update all path references using the audit from Phase 0: 1. Update path-config.json with new paths: ```json { "paths": { "manifestPath": ".sdlc/05-backlog/A-accounts/master-view/", "userStoriesPath": ".product-specs/00-platform-core/epics/EP-001-accounts/", "sessionStatePath": ".sdlc/10-project-tracking/config/", "currentWorkPath": ".sdlc/10-project-tracking/iterations/current/" } } ``` 2. Run the path update script (if created) or manually update: - Scripts that reference old paths - Any hardcoded paths in source files - README files with broken links 3. Special attention to: - run-slice.sh (critical path) - Agent prompt files (if any have paths) Report all updates made. ``` | heading_3
2025-08-16T09:29:29.177Z | Section 30 | 🔴 CHECKPOINT 8: References Updated **Type**: RED - CRITICAL TEST POINT: - [ ] Run sample script to test paths - [ ] Verify at least one agent works - [ ] Check critical scripts (run-slice.sh) - [ ] APPROVAL REQUIRED: "System functional" - [ ] DECISION POINT: Commit or rollback? --- | heading_3
2025-08-16T09:29:29.177Z | Section 31 | ✅ Phase 7: Validation | heading_2
2025-08-16T09:29:29.177Z | Section 32 | Prompt 9: Run Verification Suite ``` @cc Please verify the reorganization: 1. Run verification script: ```bash node scripts/verify-reorg.js ``` 2. Test critical paths: ```bash | heading_3
2025-08-16T09:29:29.177Z | Section 33 | Test type checking still works npm run type-check | heading_1
2025-08-16T09:29:29.177Z | Section 34 | Test processor pipeline ./scripts/run-processor-pipeline.sh test | heading_1
2025-08-16T09:29:29.177Z | Section 35 | Test slice execution ./scripts/run-slice.sh 1 ``` 3. Verify git history preserved: ```bash | heading_1
2025-08-16T09:29:29.177Z | Section 36 | Check a moved file maintains history git log --follow .product-specs/00-platform-core/epics/EP-001-accounts/features/FEA-001-master-view/stories/us-005-account-details.md ``` 4. Check for broken imports: ```bash npm run build ``` Report all test results and any failures. ``` | heading_1
2025-08-16T09:29:29.177Z | Section 37 | 🔴 CHECKPOINT 9: All Systems Go **Type**: RED - FINAL VERIFICATION: - [ ] All tests passing - [ ] Git history verified - [ ] Build successful - [ ] Manual test of one workflow - [ ] FINAL APPROVAL: "Commit changes" --- | heading_3
2025-08-16T09:29:29.177Z | Section 38 | 🎯 Phase 8: Finalization | heading_2
2025-08-16T09:29:29.177Z | Section 39 | Prompt 10: Complete Migration ``` @cc Please finalize the reorganization: 1. Clean up empty directories: ```bash find .sdlc -type d -empty -delete ``` 2. Update main README with new structure 3. Create migration log: ```bash echo "# SDLC Reorganization Log - $(date)" > .sdlc/10-project-tracking/migration-log.md echo "## Files Moved:" >> .sdlc/10-project-tracking/migration-log.md git log --name-status --oneline -20 >> .sdlc/10-project-tracking/migration-log.md ``` 4. Commit all changes: ```bash git add -A git commit -m "feat: separate product specs from SDLC process - Moved user stories to .product-specs/ - Consolidated tracking to .sdlc/10-project-tracking/ - Archived obsolete files to .sdlc/09-archive/ - Updated all path references - Maintained git history for all moves" ``` 5. Tag new structure: ```bash git tag -a post-reorg-v1.0 -m "Structure after product/SDLC separation" ``` Report completion status and any remaining tasks. ``` | heading_3
2025-08-16T09:29:29.177Z | Section 40 | ✅ CHECKPOINT 10: Migration Complete **Type**: GREEN - Celebrate! - [ ] All changes committed - [ ] New structure tagged - [ ] README updated - [ ] Team notified --- | heading_3
2025-08-16T09:29:29.177Z | Section 41 | 🚨 Emergency Rollback (If Needed) | heading_2
2025-08-16T09:29:29.177Z | Section 42 | Prompt 11: Rollback Procedure ``` @cc If anything goes wrong, execute rollback: 1. Stash any uncommitted changes: ```bash git stash ``` 2. Return to pre-reorg state: ```bash git checkout main git branch -D feature/sdlc-product-separation-2025-08 ``` 3. Restore from tag if needed: ```bash git checkout pre-reorg-v1.0 ``` Only use if critical failures occur. ``` --- *Execute prompts in order. Stop if any phase fails.* | heading_3

## Summary
Metric | Value
Report Name | reorg-execution-prompts
Sections | 42
Generated | 8/16/2025
Date | August 10, 2025
Purpose | Step-by-step prompts for safe reorganization
Type | GREEN - Celebrate!